## Sheet1
CSSE National Operations Plan
September 14.2015
Communications Committee Project Timelines
Communication Committee Restructuring |  | Responsible | Original Target | Decision Points | Adjusted Target | Status
| Evaluate current Communications Committee roles, responsibilities, leadership & which working groups are to be included within the Communication Mandate | D. Trottier | 2014-10-03 |  |  | Done
| Establish new org chart for CCE and associated working groups & circulate to stakeholders for feedback | D. Trottier | 2014-10-03 |  |  | Done
| Obtain go forward approval from Jim Hopkins, Wayne Glover and Don Ross | D. Trottier | 2014-10-20 |  |  | Done
| Define current leadership & team members for all Communication working groups | D. Trottier | 2014-11-28 |  |  | Done
| Finalize new structure and communication channel for CCE | D. Trottier | 2014-11-28 | CCE Meeting |  | Done
| Pursue team members for missing positions & fill roles | CCE | 2015-12-30 |  |  | Ongoing
| Forward current structure to BOD for their advisement | D. Ross | 2015-01-29 | BOD Meeting
| Adjust strategy according to any comments received | CCE | 2015-02-15
CRM (CSM) Project - Phase 1 - Assessment & Selection |  | Responsible | Target | Decision Points |  | Status
| Review 2013 Member Needs Survey for communications-related results | M. Reid | 2014-11-14 |  |  | Done
| Create questions for CRM-specific supplemental survey to be sent to National Leadership Team, avoiding duplication from member needs survey | M. Reid | 2014-11-21 |  |  | Done
| Review and Approve supplemental survey questions at Communications Committee meeting | Communication Committee Executive | 2014-11-28 |  |  | Done
| Establish CRM Working Group | Communication Committee Executive | 2014-11-28 | CCE Meeting |  | Done
| Survey to be completed by NLT - Send on November 28th, to be completed by December 12th. | M. Reid | 2014-12-12 |  |  | Done
| Write report outlining CRM requirements based on organizational needs & share with CRM Working Group | M. Reid | 2014-12-19 |  |  | Done
| CRM Working Group to discuss research and put forward recommendation including costs to CCE | CRM Working Group | 2015-01-19 | CCE Meeting |  | Done
| Submit recommendation to the Board of Directors for consideration at January 29th board meeting (Including rollout concept strategy for approval) | D. Ross | 2015-01-29 | BOD Meeting |  | Done
CRM (CSM) Project – Phase 2 – Implement the new CSM system to all CSSE Stakeholders |  | Responsible | Target | Decision Points |  | Status
| Review approval from January 29th board meeting. Adjust project objectives accordingly. | Communication Committee Executive | 2015-02-06 |  |  | Done
| Develop Communication CRM directive to outline use and maintenance responsibilities of the new system | CRM Working Group | 2015-02-27 |  | 2015-09-30
| Develop roll out package & assign roll out responsibilities | CRM Working Group | 2015-02-27 |  | 2015-09-30
| Approval of CRM roll out package and plan with CCE | Communication Committee Executive | 2015-03-06 | CCE Meeting
Roll out new CRM system to CSSE Stakeholders and provide training:
| a. National Board Members & CSSE Staff | CRM Working Group | 2015-03-20 |  | 2015-10-30
| b. National Chapter Presidents – to be then shared with Chapter Executive | CRM Working Group | 2015-03-27 |  | 2015-11-30
| c. National Committee Leadership – to be then shared with Committee executive and associated Working Group members | CRM Working Group | 2015-04-03 |  | 2015-12-31
| d. Others as required by the CSSE Board | CRM Working Group | Ongoing
| Review progress and obtain feedback for amendments from BOD | D. Ross | 2015-05-22 | BOD Meeting | TBD
| Review and adjust CRM Directive following roll out & engagement & report to CCE | CRM Working Group | 2015-06-15 |  | 2016-01-01
Defining the CSSE Communication Channels, Leadership Roles & Responsibilities |  | Responsible | Target | Decision Points |  | Status
| Research current CSSE communication channels with all levels of leadership (Board, Chapters, Committees, Staff) | Strategy Working Group | 2014-12-30 |  | 2015-10-31
| Establish Communication Channel Graphic (s) to depict current situation | Strategy Working Group | 2015-01-15 |  | 2015-10-31
| Present & Discuss current situation with CCE and identify opportunities for improvement - formalize strategy forward | Communication Committee Executive | 2015-01-19 | CCE Meeting | October Meeting
| Submit current understanding to BOD for comment | D. Ross | 2015-01-29 | BOD Meeting | TBD
| Develop new CSSE communication channel strategy directive - establish roles & responsibilities for leadership (Board, Chapter, Committees, Staff) | Strategy Working Group | 2015-03-15 |  | 2015-11-30
| Present CSSE communication channel strategy directive to CCE | Strategy Working Group | 2014-04-30 | CCE Meeting | 2015-12-31
| Present CSSE communication channel strategy directive to BOD for approval | D. Ross | 2015-05-22 | BOD Meeting | TBD
| Roll out CSSE Communication Channel directive to CSSE Stakeholders | Strategy Working Group | 2015-04-03 |  | 2016-02-01
| Review & adjust directive following roll out and engagement | Strategy Working Group | 2015-08-30 |  | 2016-06-01
Research & Information Resource |  | Responsible | Target | Decision Points |  | Status
| Reach out to academia and request for additional articles for Journal publication | Journal Working Group | 2015-01-30 |  | 2015-10-01
| Develop communication & distribution process for position papers, white papers and briefing notes and submit to BOD | Journal Working Group | 2016-01-30 |  | 2015-12-31
ADD MARKeting strategy here