## Sheet1
STATUS | TASK TITLE | TASK OWNER | TASK DESCRIPTION
2-1.5 MONTHS BEFORE EVENT
☐ | Put together team |  | Assemble group of motivated young female activists to work together
☐ | Determine date | Event Coordinator | Decide whether event will be on October 11th or close to October 11th
☐ | Create messaging | Media Coordinator | Develop event's objectives and other communications messaging
☐ | Reserve venue | Event Coordinator | Research and select venue; contact the appropriate people to reserve space
☐ | Contact govt officials | Outreach Coordinator | Reach out to all officials you would like to attend with official date, time, and event description
☐ | Identify interested groups | Outreach Coordinator | Research which local groups might be interested in attending and reach out to them
☐ | Idenity emcee | Volunteer Coordinator | Pick members of the organizing team (or other volunteers) to emcee the event
☐ | Reach out for gifts | Volunteer Coordinator | If there will be a raffle, reach out to local businesses for donations
1 MONTH-2 WEEKS BEFORE EVENT
☐ | Check and order supplies | Event Coordinator | Check if you have any of the supplies necessary for the event, order if not (you could even order DotG-US merch)
☐ | Obtain confirmation from all guests | Outreach Coordinator | Finalize list of government officials who will be attending the event
☐ | Create program | Event Coordinator | If there will be a paper program to hand out at your event, complete it in advane
☐ | Create online event page | Outreach Coordinator | Allow people to start reserving seats through an online event page (e.g. eventbrite)
☐ | Publicize! | Media Coordinator | However you will be advertising, begin doing so! Hang up flyers, post online, etc.
☐ | Ensure venue has setup info | Event Coordinator | If there are any set-up needs (sound systems, etc), confirm that the venue has that info
☐ | Post transportation/parking info | Outreach Coordinator | Ensure that directions, transportation, and parking information is accessible online
☐ | Recruit volunteers to support event | Volunteer Coordinator | Have volunteers to hand out programs, lead people to seats, man microphones, livestream, introduce guests, etc.
☐ | Contact local media | Media Coordinator | Reach out to members of the press from local papers, TV stations, and radio stations with press release
1 WEEK BEFORE EVENT
☐ | Set up question box at school/s | Event Coordinator | Set up box for students to submit their questions at your school/several local schools
☐ | Confirm reservation with venue | Event Coordinator | Contact the venue the confirm that the event is still on
☐ | Continue to publicize | Media Coordinator | Continue to advertise the event online
☐ | Follow up with media | Media Coordinator | Remind all the contact members of the media a day before the event to come
☐ | Ensure that you have contact info | Volunteer Coordinator | Confirm that you have every volunteer's contact information written down and in your phone
☐ | Ensure that you have enough vols | Volunteer Coordinator | Make sure you have enough volunteers to run the event, and if not do some quick recruiting
☐ | Print all the programs | Event Coordinator | Print the programs for the event
☐ | Provide venue with number of RSVPs | Outreach Coordinator | Reach out to venue with the number of people who have responded on eventbrite, facebook, etc.
DAY OF EVENT
☐ | Arrive two hours before event | Everyone | All volunteers and leaders should begin setting up at least two hours before the doors will be opening to the public
☐ | Ensure all vols know their jobs | Volunteer Coordinator | Make sure all volunteers know and understand their responsibilities during the event
☐ | Mark all reserved seats | Outreach Coordinator | Mark seats for all people who reserved seats online
☐ | Print list of registered guests | Outreach Coordinator | When registered guests arrive they can have their names crossed off this list (some may be press)
☐ | Provide volunteers with name tags | Volunteer Coordinator | Name tags will make the leadership and volunteers more officials
☐ | Post, post, post! | Media Coordinator | Be posting on social media before and throughout the event! A volunteer should livestream.
☐ | Meet and escort govt officials | Event Coordinator | Take officials to where they will be waiting backstage and give them a run-through of the event
☐ | Conference with emcee | Volunteer Coordinator | Talk to emcee about hosting the event and coordinating who will ask questions when
☐ | Talk with press | Media Coordinator | Talk with all present members of the press about the event (have solid talking points)
☐ | Estimate number of attendees | Event Coordinator | In whatever way makes sense to you, try to get an estimate of how many people attended the event
AFTER THE EVENT
☐ | Sent event summary and photos to press | Media Coordinator | Any press who didn't attend should receive an email the following day with a summary, quotes, and photos
☐ | Send thank you cards to govt officials | Outreach Coordinator | Formally thank all the guests for coming and answering the public's questions
☐ | Send thank yous to all volunteers | Volunteer Coordinator | Thank all the volunteers who made the event possible even after the event is over!
☐ | Send thank you to the venue | Event Coordinator | Thank the venue for hosting!
☐ | Debrief as a team | Everyone | Celebrate your sucess and debrief about how you feel it went and how future events could be stronger