SEVEN STEPS TO DEVELOP A PROJECT TIMELINE

- DEFINE WHAT YOU ARE PRODUCING & WHAT SUCCESS LOOKS LIKE.

- WHEN MUST THE PRODUCT BE COMPLETELY FINISHED?

- WORK BACKWARDS FROM THAT END DATE.

- BREAK THE PROJECT DOWN INTO SMALL STEPS.

- PUT THE STEPS INTO A TIMELINE:  TASKS, PEOPLE, DEADLINES.

  - WHAT HAS TO BE DONE FIRST, BEFORE YOU CAN MOVE ON TO THE NEXT STEP, AND SO ON?

  - HOW LONG WILL IT TAKE TO COMPLETE EACH STEP?  ALLOW SOME WIGGLE ROOM.

  - WHO IS RESPONSIBLE FOR COMPLETING EACH STEP?

  - WHEN MUST/WILL DECISIONS BE MADE ON EACH STEP?

  - WHEN ARE YOUR MEETINGS?  CAN YOU DELEGATE DECISIONS TO INDIVIDUALS, OR MAKE THEM ONLINE?

- WHEN SOMETHING DOESN’T HAPPEN ON SCHEDULE:

  - REVISE THE REST OF THE TIMELINE TO COMPLETION.

  - EITHER THE DUE DATE WILL HAVE TO BE POSTPONED, OR OTHER STEPS WILL HAVE TO BE DONE MORE QUICKLY THAN PLANNED.

- REMEMBER:  FAST, CHEAP, AND GOOD.  YOU CAN ONLY GET 2 OUT OF 3.  FAST AND GOOD WILL COST MORE.  GOOD AND CHEAP WILL TAKE LONGER.

Name of project:

| Item/Person | SEPT | OCT | NOV | DEC |
| --- | --- | --- | --- | --- |

Name of project:   Handout

| Item/Person | SEPT | OCT | NOV | DEC |
| --- | --- | --- | --- | --- |
| Begin search for photos and graphics |  |  | 11/1 |  |
| Ideas for copy go to writer |  |  | 11/1 |  |
| Draft copy goes to committee for comments |  |  | 11/8 |  |
| Comments due from committee |  |  | 11/15 |  |
| Deliver final copy and art to designer |  |  |  | 11/22 |
| Deliver art and money to printer |  |  |  | 12/1 |
| Pick up from printer |  |  |  | 12/15 |